Head of Planning

East Sussex County Council

St. Anne’s Crescent

County Hall

Lewes

BN7 1UE

Our Reference: SL/B2H/1.4.1/0338

Dear Sir,

**Town and Country Planning Act 1990 Relating to land known as A259 Belle Hill,**

**Bexhill on Sea to B2092 Queensway, St. Leonards on Sea, East Sussex RR/2474/CC(EIA) – Condition 11 (Out of Hours Working).**

We are writing to request out of hours working related to the essential tie-in works at the junction between Queensway and the new link road and the Crowhurst Road junction with Queensway. The requested dates and times are as follows:

* Monday 17th August 19:00hrs – Tuesday 18th August 05:00hrs;
* Tuesday 18th August 19:00hrs – Wednesday 19th August 05:00hrs;
* Wednesday 19th August 19:00hrs – Thursday 20th August 05:00hrs;
* Thursday 20th August 19:00hrs – Friday 21st August 05:00hrs;
* Friday 21st August 19:00hrs – Saturday 22nd August 05:00hrs;
* Saturday 22nd August 19:00hrs – Sunday 23rd August 05:00hrs;
* Sunday 23rd August 19:00hrs – Monday 24th August 05:00hrs;
* Monday 24th August 19:00hrs – Tuesday 25th August 05:00hrs;
* Tuesday 25th August 19:00hrs – Wednesday 26th August 05:00hrs;
* Wednesday 26th August 19:00hrs – Thursday 27th August 05:00hrs;
* Thursday 27th August 19:00hrs – Friday 28th August 05:00hrs;
* Friday 28th August 19:00hrs – Saturday 29th August 05:00hrs;
* Tuesday 01st September 19:00hrs – Wednesday 02nd September 05:00hrs;
* Wednesday 02nd September 19:00hrs – Thursday 03rd September 05:00hrs;
* Thursday 03rd September 19:00hrs – Friday 04th September 05:00hrs;
* Friday 04th September 19:00hrs – Saturday 05th September 05:00hrs;
* Saturday 05th September 19:00hrs – Sunday 06th September 05:00hrs (as a contingency); and
* Sunday 6th September 19:00hrs – Monday 7th September 05:00hrs (as a contingency).

The reason the works are proposed to be carried out during the above hours is to minimise the disruption caused to the local road users. Similarly, carrying out these works over continuous nights will reduce the disruption caused over the remainder of the project. Due to the extent of the tie-in works, especially with regards to the road surfacing, the works will be of a noisy nature. However, in order to reduce the impact on local residents we are proposing the following:

* Traffic Management to start to be put out at 19:00hrs;
* Planing works to stop by 00:00hrs;
* Reinstatement works to be completed by 03:00hrs; and
* Traffic Management to be removed by 05:00hrs.

The planned plant and equipment involved in the above operations shall be as follows:

HTW:

* 1 x 6t 360 Excavator with breaker;
* 1x 9t Dump truck;
* 4 x Light towers;
* 1x Transit van;
* 1x Road sweeper;
* 1x Floor saw;
* 1x Hydraulic breaker pack; and
* Small tools.

Conway:

* 1x Paver;
* 1x Planer;
* 2x Rollers;
* 1x JCB street master;
* 10+ Lorries;
* 1x Road sweeper; and
* Small tools

The planned resources involved in the above operations shall be as follows:

HTW:

* 1x Supervisor;
* 1x 360 Excavator operator;
* 1x Dump truck driver;
* 2x General operatives; and
* 1x Banksman.

Conway:

* 1x Paving Gang; and
* Associated drivers.

A letter drop will be carried out to the residents in the vicinity of these proposed works.

There will be proposed artificial lighting used as outlined above, but these will be placed in such a position that they face away from local residents.

This application is made on behalf of the Assistant Director – Transport and Operations, East Sussex County Council and the relevant cost code for payment of fees due is C.5.04.200.2.

We trust that our proposals meet with your approval.

Yours faithfully,

Kim Barrows

Project Manager

For the Hochtief – Taylor Woodrow Joint Venture

On behalf of East Sussex County Council

Cc Bob Pape / File