Kim Barrows, Project Manager

Hochtief - Taylor Woodrow Joint Venture,

Bexhill to Hastings Link Road Site Offices,

Crowhurst Road,  Upper Wilting Farm

St Leonards on Sea TN38 8EG

Date:

28 August 2015

please contact	our ref	your ref

Mrs Sarah Iles	RR/2474/CC(EIA)	SL/B2H/1.4.1/0344

01273 481631		JH/SLI

sarah.iles@eastsussex.gov.uk

Dear Mr Barrows

RR/2474/CC(EIA) – CONSTRUCTION OF A NEW ROAD, INCLUDING ENVIRONMENTAL TREATMENT WITH EARTHWORKS, PLANTING, FLOOD AND NOISE ATTENUATION, WILDLIFE COMPENSATION, AND FACILITIES FOR NON-MOTORISED USERS. A259 BELLE HILL, BEXHILL-ON-SEA TO B2092 QUEENSWAY, ST LEONARDS-ON-SEA (KNOWN AS THE BEXHILL-HASTINGS LINK ROAD)

CONDITION 11 - CONSTRUCTION HOURS

I refer to your letter dated 26 August 2015, requesting approval to undertake works outside the approved hours, in relation to the above development.  For clarification, the approved hours for construction activities under Condition 11 are currently 7am – 7pm Mondays to Fridays and 7am – 1pm on Saturdays.  No working is permitted on Sundays, Bank or Public Holidays.

Current variations to these hours cover:  1) the period until 4 October 2015 for works being undertaken (i) in the rural section (Ch 1600-5500) on Mondays to Fridays, between the hours of 19.00 and 20.00; (ii) in the urban and rural areas on Saturdays, between the hours of 13.00 and 18.00; and (iii) in the rural section (Ch 1600-5500) on Sundays between the hours of 09.00 and 18.00; and 2) various dates until 7 September 2015 for tie-in works at the junction between Queensway and the new Link Road and the Crowhurst Road junction with Queensway, between the hours of 19.00 and 05.00.  These additional hours were both subject to separate approvals on 7 August 2015.

/Continued

-2-	28 August 2015

You are now seeking approval to carry out surfacing works between the hours of 19.00 and 05.00 from Wednesday 16th until Saturday 19th September 2015, and between the hours of 18.00 and 00.00 on Saturday 19th/Sunday 20th September 2015 (as a contingency).  The surfacing works will take place between Ch.4600 and Ch.5500.  However, in order to minimise disruption to local residents, it is only proposed to work until 05.00 hours between Ch.4600 (Decoy) and Ch.5200 (Crowhurst Road).  Works between Ch.5200 (Crowhurst Road) and Ch.5500 (Queensway) will finish by 00.00 hours on each day.

You have indicated that the reason for the request to work outside the hours specified in Condition 11 of the planning permission is to mitigate delays to the programme caused by the recent inclement weather, and to ensure the carriageway surfacing is laid in time for the 10k run, which is due to take place on Sunday 20th September 2015.

You have confirmed that artificial lighting will be used, but that it will be placed in such a position so as to face away from any residential properties.  You have also confirmed that local residents in the vicinity of the proposed works will be notified of the works to be carried out during these additional hours.  Please ensure that the letter drop includes the residential properties immediately to the east of the Queensway.

The planned resources, plant and equipment to be used for the proposed works will be as follows:

| HTW: 1 x 6t 360 Excavator with breaker; 1x 9t Dump truck; 4 x Light towers; 1x Transit van; 1x Road sweeper; 1x Floor saw; 1x Hydraulic breaker pack; and Small tools. | 1x Supervisor; 1x 360 Excavator operator; 1x Dump truck driver; 2x General operatives; and 1x Banksman. |
| --- | --- |

| Conway: 1x Paver; 2x Rollers; 1x JCB street master; 10+ Lorries; 1x Road sweeper; and Small tools | 1x Paving Gang; and Associated drivers. |
| --- | --- |

/Continued

-3-	28 August 2015

I have given consideration to this request and taken into account the nature of the works proposed and the potential impact of the works on the amenity of local residents.  It is noted that these works are proposed to be undertaken extending into what are considered to be particularly unsociable hours and there are concerns regarding the potential adverse impact on residential amenity.  However, the need for them to be carried out to ensure the surfacing works are completed in time for the 10k run and to mitigate delays in the program is recognised.  Consequently, I have reviewed the length of time you have requested, and the measures to reduce the impact on local residents, and consider that there is scope for these works to be undertaken outside of the construction hours approved under condition 11.

Therefore, in relation to the planning permission solely, in accordance with the powers delegated to me and pursuant to the provisions of condition 11, I hereby APPROVE the surfacing works between Ch.4600 and Ch.5500, as detailed in your letter and referred to above, being carried out between the following hours:

Between Ch.4600 (Decoy) and Ch.5200 (Crowhurst Road):

- Wednesday 16th September (19:00hrs) – Thursday 17th September (05:00hrs);

- Thursday 17th September (19:00hrs) – Friday 18th September (05:00hrs);

- Friday 18th September (19:00hrs) – Saturday 19th September (05:00hrs); and

- Saturday 19th September (18:00hrs) – Sunday 20th September (00:00hrs) – (as a contingency).

Between Ch.5200 (Crowhurst Road) and Ch.5500 (Queensway):

- Wednesday 16th September (19:00hrs) – Thursday 17th September (00:00hrs);

- Thursday 17th September (19:00hrs) – Friday 18th September (00:00hrs);

- Friday 18th September (19:00hrs) – Saturday 19th September (00:00hrs); and

- Saturday 19th September (18:00hrs) – Sunday 20th September (00:00hrs) – (as a contingency).

For the avoidance of doubt, works between Ch.5200 (Crowhurst Road) and Ch.5500 (Queensway) must cease by 00.00 hours.  Therefore, between the hours of 00.00 and 05.00, works are only permitted between Ch.4600 (Decoy) and Ch.5200 (Crowhurst Road).

Any additional working arrangements outside the approved hours detailed above for planning permission purposes, or for works not listed above, will be subject to further review and will require agreement in writing from the Head of Planning and Environment.

Please note that if at any time these works outside the approved construction hours gives rise to justifiable complaint, or harm to amenity, I reserve the right to withdraw this temporary approval.  Please also note that should you received any complaints, you should notify Sarah Iles on Lewes (01273) 481631 within two working days of receiving the complaint.

Yours sincerely

Tony Cook

Tony Cook

Head of Planning and Environment

- Copy for Statutory Planning Register c/o Hastings Borough Council and Rother District Council, Your Ref RR/07/1488 - HS/07/444

- Amanda Parks Technical Assistant

- Bob Pape – East Sussex County Council (via email only)

- Chloe DeRenzy-Martin – East Sussex County Council (via email only)

condapprove.doc