Kim Barrows, Project Officer

BHLR Site Offices

Crowhurst Road

Upper Wilting Farm

St Leonards on Sea

East Sussex TN38 8EG

Date:

8 October 2015

please contact	our ref	your ref

Mrs Sarah Iles	RR/2474/CC(EIA)	SL/B2H/1.4.1/0356

01273 481631		JH/SLI

sarah.iles@eastsussex.gov.uk

Dear Mr Barrows

RR/2474/CC(EIA) – CONSTRUCTION OF A NEW ROAD, INCLUDING ENVIRONMENTAL TREATMENT WITH EARTHWORKS, PLANTING, FLOOD AND NOISE ATTENUATION, WILDLIFE COMPENSATION, AND FACILITIES FOR NON-MOTORISED USERS. A259 BELLE HILL, BEXHILL-ON-SEA TO B2092 QUEENSWAY, ST LEONARDS-ON-SEA (KNOWN AS THE BEXHILL-HASTINGS LINK ROAD)

CONDITION 11 - CONSTRUCTION HOURS

I refer to your letter dated 6 October 2015, requesting approval to undertake works outside the approved hours, in relation to the above development.  For clarification, the approved hours for construction activities under Condition 11 are currently 7am – 7pm Mondays to Fridays and 7am – 1pm on Saturdays.  No working is permitted on Sundays, Bank or Public Holidays.

The only current variation to these hours covers the period until 18 October 2015 for works being carried out in connection with the gabion walls to the south of Ninfield Road Overbridge, on Sundays between the hours of 09.00 and 1600.  These additional hours were subject to separate approval on 24 September 2015.  A further request for out of hours working in the urban and rural areas of the Scheme was submitted on 25 September 2015 and will be considered separately.

You are now seeking approval to carry out works in the vicinity of the Ninfield Road Overbridge on Tuesday 13, Wednesday 14 and Thursday 15 October 2015, between the hours of 19.00 and midnight, and on Friday 16 October 2015 between the hours of 19.00 and midnight (as a contingency).  The works are in relation to the surfacing of the bridge deck and approaches to Ninfield Road Overbridge.

/Continued

-2-	8 October 2015

You have indicated that the reason for the request to work outside the hours specified in Condition 11 of the planning permission is to provide a safe working area for the surfacing contractors.  Also, as there is a very busy junction at this location, the disruption to local road users will be minimised.

You have also indicated that some of the works will be of a noisy nature and, in order to help minimise disruption and disturbance to local residents, the following constraints on activities/hours are proposed:

- Traffic Management to start to be put out at 19:00hrs;

- Planing works to stop by 23:00hrs;

- Reinstatement works to be completed by 23:00hrs; and

- Traffic Management to be removed by 00:00hrs.

You have confirmed that additional artificial lighting will not be used and that local residents in the vicinity of the proposed works will be notified of the works to be carried out during these additional hours.

The planned works relate to kerbing, which will involve removing the existing kerbs to the traffic island at the Wrestwood Road junction, and a length of kerb line to the adjacent footway, and providing new kerbs for this island.  These works will involve an element of ‘breaking’ out in order to remove the kerbs.

The planned plant, equipment and resources for these works are as follows:

- 1no Site Supervisor;

- 2no Operatives;

- 1no Engineer;

- 2no Site Vehicles;

- 1no Floor Saw;

- Breaking out tools.

The planned works also relate to surfacing, which will involve:  (i) planing out the existing ‘wearing course’ on the road near to the BP garage and up to the traffic island on Wrestwood Road, and part way onto Elva Way and a little way up Ninfield Road; (ii) providing a ‘surface course’ to the planed out areas and the bridge deck; and (iii) placing the surface course once the planing has been completed.

The planned plant, equipment and resources for these works are as follows:

| 1no. Site Supervisor; 2no. Gangers; 6no. Operatives; 1no. Banksman; 1no. Planer; 1no. Sweeper; 1no. Paver; | 1no. Paver; 1no. HD90 roller; 1no. TR140 roller; 1no. JCB Streetmaster; 1no. Tack coat lorry; Material wagons; and 1no. Lining rig. |
| --- | --- |

White lining is also to be applied and this will require an additional vehicle and operatives to undertake this work.

/Continued

-3-	8 October 2015

I have given consideration to this request and taken into account the nature of the works proposed and the potential impact of the works on the amenity of local residents.  It is noted that these works are proposed to be undertaken extending into what are considered to be unsociable hours and there are concerns regarding the potential adverse impact on residential amenity.  However, the need for them to be carried out during times to minimise disruption to local road users and provide a safe working environment is recognised.  Consequently, I have reviewed the length of time you have requested, and the measures to reduce the impact on local residents, and consider that there is scope for these works to be undertaken outside of the construction hours approved under condition 11.

Therefore, in relation to the planning permission solely, in accordance with the powers delegated to me and pursuant to the provisions of condition 11, I hereby APPROVE the works in the vicinity of the Ninfield Road Overbridge as detailed in your letter, and referred to above, being carried out between the following hours:

- Tuesday 13 October 2015: 19:00hrs – midnight;

- Wednesday 14 October 2015: 19:00hrs – midnight;

- Thursday 15 October 2015: 19:00hrs – midnight; and

- Friday 16 October 2015: 19:00hrs – midnight (as a contingency).

For the avoidance of doubt, planing, reinstatement works, and any other noisy works must cease by 23.00 hours.

Please note that this approval relates SOLELY to the reinstatement of the surfacing of the bridge deck and approaches in the vicinity of the Ninfield Road Overbridge.  Any additional working arrangements outside the approved hours detailed above, or for works not listed above, will be subject to further review and will require separate agreement in writing from the Head of Planning and Environment.

Finally, please note that if at any time the activities being carried out in these extended hours give rise to justifiable complaint, or demonstrable harm to amenity, I reserve the right to withdraw this temporary amendment to the permitted working hours.  Please also note that should you received any complaints, you should notify Sarah Iles on Lewes (01273) 481631 within two working days of receiving the complaint.

Yours sincerely

Tony Cook

Tony Cook

Head of Planning and Environment

- Copy for Statutory Planning Register c/o Hastings Borough Council and Rother District Council, Your Ref RR/07/1488 - HS/07/444

- Amanda Parks Technical Assistant

- Bob Pape – East Sussex County Council (via email only)

- Chloe DeRenzy-Martin – East Sussex County Council (via email only)

condapprove.doc