Richard Wall-Morris - Project Manager

Hochtief - Taylor Woodrow Joint Venture (BHLR)

Site Offices

Upper Wilting Farm

Crowhurst Road

St Leonards-on-Sea  East Sussex  TN38 8EG

Date:

4 April 2014

please contact	our ref	your ref

Mrs Sarah Iles	RR/2474/CC(EIA)	SL/B2H/1.4.1/0214

01273 481631		GM/SLI

sarah.iles@eastsussex.gov.uk

Dear Mr Wall-Morris

RR/2474/CC(EIA) – CONSTRUCTION OF A NEW ROAD, INCLUDING ENVIRONMENTAL TREATMENT WITH EARTHWORKS, PLANTING, FLOOD AND NOISE ATTENUATION, WILDLIFE COMPENSATION, AND FACILITIES FOR NON-MOTORISED USERS. A259 BELLE HILL, BEXHILL-ON-SEA TO B2092 QUEENSWAY, ST LEONARDS-ON-SEA (KNOWN AS THE BEXHILL-HASTINGS LINK ROAD)

CONDITION 11 - CONSTRUCTION HOURS

I refer to your letter dated 26 March 2014, requesting approval to undertake works outside the approved hours, in relation to the above development.  For clarification, the approved hours for construction activities under Condition 11 are currently 7am – 7pm Mondays to Fridays and 7am – 1pm on Saturdays.  No working is permitted on Sundays, Bank or Public Holidays.  The only current variation to these hours is the work being undertaken for the rebuilding of Adams Farm Barn between the hours of 13.00 and 17.00 on Saturdays and between 09.00 and 17.00 on Sundays, which was subject to separate approval on 27 February 2014.  However, this approval for extended working hours at Adams Farm expires on 20 April 2014.

You are now seeking an extension to the approved hours until 29 June 2014 as follows:

Mondays to Fridays 19.00 – 20.00;

Saturdays 13.00 – 19.00; and

Sundays 09.00 – 18.00.

/Continued

-2-	4 April 2014

The locations and works proposed to be undertaken during these additional hours are as follows:

Urban Section:

- Drainage, earthworks, pavement, kerbing and ducting installation works between Belle Hill and Ninfield road;

- Works on Woodsgate Park Overbridge and Ninfield Road Overbridge.

Rural Section:

- Cut, fill and topsoil strip earthworks at Combe Haven, Actons Farm, Watermill, Hillcroft Farm, Powdermill, Adams Farm, Decoy Pond, Upper Wilting and Queensway.

- Works on Combe Haven Underbridge, Watermill Stream Underbridge, Decoy Pond Underbridge and Railway Bridge;

- Haul route maintenance from Elva Way to Crowhurst Road; and

- General plant maintenance in all areas between Elva Way to Crowhurst Road.

You have indicated that the reason for the request is to mitigate the delays encountered from the recent adverse weather conditions.  In respect of the additional hours requested, you have confirmed that on Sundays it is only intended to undertake earthworks in the rural section of the scheme (Ch.2000 – 5400) and that no works will be carried out in the urban section during these hours.

You have confirmed that local residents will be notified of the intended works in advance of them taking place.

I have given consideration to this request and taken into account the nature of the delays, the works proposed and the potential impact of the works on the amenity of local residents and recreational users of the area, as well as the original reason for this condition.  All these factors have to be balanced.  The reason for Condition 11 is to safeguard rural and residential amenities in the vicinity of the site.  As a result, I do not consider it appropriate to approve your request in full.

However, in order to provide some flexibility regarding the delays in the construction programme due to the adverse weather conditions, I have considered separately allowing certain works to be undertaken outside the approved hours.

I have also considered the length of time you have requested.  Consequently, in accordance with the powers delegated to me and pursuant to the provisions within Condition 11 of the above planning permission, I hereby APPROVE the following additional hours of working to be undertaken until 29 June 2014:

- Mondays to Fridays 19.00 – 20.00 – ONLY in the rural section (Ch.2000-5400);

- Saturdays 13.00 – 18.00; and

- Sundays 09.00 – 18.00 – ONLY in the rural section (Ch.2000-5400).

/Continued

-3-	4 April 2014

Any additional working arrangements outside the approved hours beyond 29 June 2014, or for works not listed above, will be subject to further review and will require agreement in writing from the Head of Planning.

In recognition of amenity constraints, and for clarity and the avoidance of doubt, in accordance with the powers delegate to me, I hereby do NOT APPROVE the particular request for works to be undertaken as follows:

- Between the hours of 19.00 and 20.00 on Mondays to Fridays in the urban section of the development;

- Between the hours of 18.00 and 19.00 on Saturdays; and

- No works are permitted in the urban section of the development on Sundays.

Please note that if at any time the activities being carried out in these extended hours give rise to justifiable complaint, or demonstrable harm to amenity, I reserve the right to withdraw this temporary amendment to the permitted working hours.  Please also note that should you received any complaints, you should notify Sarah Iles on Lewes (01273) 481631 within two working days of receiving the complaint.

Yours sincerely

Tony Cook

Tony Cook

Head of Planning

- Copy for Statutory Planning Register c/o Hastings Borough Council and Rother District Council, Your Ref RR/07/1488 - HS/07/444

- Amanda Parks Technical Assistant

- Bob Pape – East Sussex County Council (via email only)

- Chloe DeRenzy-Martin – East Sussex County Council (via email only)

condapprove.doc