Richard Wall-Morris

Hochtief - Taylor Woodrow Joint Venture

Bexhill to Hastings Link Road

Site Offices, Crowhurst Road

Upper Wilting Farm

St Leonards on Sea, TN38 8EG

Date:

23 May 2014

please contact	our ref	your ref

Mrs Sarah Iles	RR/2474/CC(EIA)	SL/B2H/1.4.1/0229

01273 481631		GM/SLI

sarah.iles@eastsussex.gov.uk

Dear Mr Wall-Morris

RR/2474/CC(EIA) – CONSTRUCTION OF A NEW ROAD, INCLUDING ENVIRONMENTAL TREATMENT WITH EARTHWORKS, PLANTING, FLOOD AND NOISE ATTENUATION, WILDLIFE COMPENSATION, AND FACILITIES FOR NON-MOTORISED USERS. A259 BELLE HILL, BEXHILL-ON-SEA TO B2092 QUEENSWAY, ST LEONARDS-ON-SEA (KNOWN AS THE BEXHILL-HASTINGS LINK ROAD)

CONDITION 11 - CONSTRUCTION HOURS

I refer to your letter dated 22 May 2014, requesting approval to undertake works outside the approved hours, in relation to the above development.  For clarification, the approved hours for construction activities under Condition 11 are currently 7am – 7pm Mondays to Fridays and 7am – 1pm on Saturdays.  No working is permitted on Sundays, Bank or Public Holidays.  Current variations to these hours cover the period until 29 June 2014 for works being undertaken in the rural section (Ch. 2000-5400) on Mondays to Fridays between the hours of 19.00 – 20.00; on Saturdays between the hours of 13.00 – 18.00 in the rural and urban sections; and on Sundays in the rural section (Ch. 2000-5400) between the hours of 09.00 – 18.00.  These additional hours were subject to separate approval on 4 April 2014.  Further approval for out of hours working at the Belle Hill end of the Scheme was also granted on 16 May 2014, and this expires at 04.00 on Saturday, 24th May 2014.

You are now seeking an extension to the approved hours, specifically from Tuesday 27th May until Saturday 31st May, Monday 2nd June until Saturday 7th June and Monday 16th June until Saturday 21st June 2014, between the hours of 19.00 and 04.00 for a part of the site within the urban section.  The works are proposed to be carried out during these hours in order to minimise the disruption caused to the local road users.  The proposed works are to continue with the tie-in works that need to be carried out at Belle Hill Junction and London Road.  In order to help minimise disruption to local residents, the following constraints on activities/hours are proposed:

- Traffic Management to start to be put out at 20:00hrs;

- Planing works to stop by 00:00hrs;

- Reinstatement works and to be completed by 02:00hrs; and

- Traffic Management to be removed by 04:00hrs.

The road planings arising from the operations will be taken and stored at the 1066 Yard within the site.  You have confirmed that artificial lighting will be used in the 1066 Yard and that these will be positioned with the light facing away from any residential properties.  A set of lights will be on standby at the junction where resurfacing will take place and, if used, will also be set up to minimise disruption.  The planned resources for these works are as follows:

- 1no. HTW Supervisor;

- 5no. Traffic Management Operatives;

- 15no. Tarmac Operatives;

- 2no. White Lining Operatives;

- 2no. Anti-skid Operatives; and

- 2no. Loop Cutting Operatives.

The plant and equipment to be used for the proposed works will be as follows:

- 1no. Excavator with breaker;

- Floor saws;

- Stihl saws;

- 1no. road planer;

- 1no. tarmac paver;

- 1no. roller;

- 2no. road wagons;

- Tarmac delivery lorries;

- Dumpers; and

- Transit vans.

You have further confirmed that local residents in the vicinity of the proposed works will be notified of the works in advance of them taking place.

I have given consideration to this request and taken into account the nature of the works proposed and the potential impact of the works on the amenity of local residents.  It is noted that these works are proposed to be undertaken extending into what are considered to be particularly unsociable hours and there are concerns regarding the potential adverse impact on residential amenity.  However, the need for them to be carried out during times to minimise disruption to local road users is recognised.  Consequently, I have reviewed the length of time you have requested and consider that there is scope for these works to be undertaken outside of the construction hours approved under condition 11.   Therefore under the powers delegated to me pursuant to condition 11, I hereby APPROVE the works at Belle Hill Junction and London Road as detailed in your letter, and referred to above, being carried out between the following hours:

/Continued

Phase 4 – West Bound:

- Tuesday 27th May 19:00hrs – Wednesday 28th May 04:00hrs;

- Wednesday 28th May 19:00hrs – Thursday 29th May 04:00hrs;

- Thursday 29th 19:00hrs – Friday 30th May 04:00hrs; and

- Friday 30th May 19:00hrs – Saturday 31st May 04:00hrs.

Phase 5 – East Bound:

- Monday 2nd June 19:00hrs – Tuesday 3rd June 04:00hrs;

- Tuesday 3rd June 19:00hrs – Wednesday 4th June 04:00hrs;

- Wednesday 4th June 19:00hrs – Thursday 5th June 04:00hrs;

- Thursday 5th June 19:00hrs – Friday 6th June 04:00hrs;

- Friday 6th June 19:00hrs – Saturday 7th June 04:00hrs;

- Monday 16th June 19:00hrs – Tuesday 17th June 04:00hrs;

- Tuesday 17th June 19:00hrs – Wednesday 18th June 04:00hrs;

- Wednesday 18th June 19:00hrs – Thursday 19th June 04:00hrs;

- Thursday 19th June 19:00hrs – Friday 20th June 04:00hrs; and

- Friday 20th June 19:00hrs – Saturday 21st June 04:00hrs.

For the avoidance of doubt, planing works must cease by 00.00 hours, reinstatement works to be completed by 02.00hours and therefore between the hours of 02.00 and 04.00, the only activities permitted are those involving the removal of the traffic management measures and clearing the site away.

Due to the proximity of residential properties, activities at the 1066 Yard should be kept to a minimum and operatives should ensure that the tipping of the planings does not cause excessive noise, particularly in relation to the tail gate on lorries banging shut.

Please note that if at any time these works outside the approved construction hours gives rise to justifiable complaint, or harm to amenity, I reserve the right to withdraw this temporary approval.  Please also note that should you received any complaints, you should notify Sarah Iles on Lewes (01273) 481631 within two working days of receiving the complaint.

Yours sincerely

Tony Cook

Tony Cook

Head of Planning

- Copy for Statutory Planning Register c/o Hastings Borough Council and Rother District Council, Your Ref RR/07/1488 - HS/07/444

- Amanda Parks Technical Assistant

- Bob Pape – East Sussex County Council (via email only)

- Chloe DeRenzy-Martin – East Sussex County Council (via email only)

condapprove.doc