Richard Wall-Morris

Hochtief - Taylor Woodrow Joint Venture

BHLR Project Team

Site Offices, Crowhurst Road

Upper Wilting Farm

ST LEONARDS-ON-SEA TN38 8EG

Date:

24 October 2014

please contact	our ref	your ref

Mrs Sarah Iles	RR/2474/CC(EIA)	PH/B2H/1.4.1/255

01273 481631		GM/SLI

sarah.iles@eastsussex.gov.uk

Dear Mr Wall-Morris

RR/2474/CC(EIA) – CONSTRUCTION OF A NEW ROAD, INCLUDING ENVIRONMENTAL TREATMENT WITH EARTHWORKS, PLANTING, FLOOD AND NOISE ATTENUATION, WILDLIFE COMPENSATION, AND FACILITIES FOR NON-MOTORISED USERS. A259 BELLE HILL, BEXHILL-ON-SEA TO B2092 QUEENSWAY, ST LEONARDS-ON-SEA (KNOWN AS THE BEXHILL-HASTINGS LINK ROAD)

CONDITION 11 - CONSTRUCTION HOURS

I refer to your letter dated 24 October 2014, requesting approval to undertake works outside the approved hours, in relation to the above development.  For clarification, the approved hours for construction activities under Condition 11 are currently 7am – 7pm Mondays to Fridays and 7am – 1pm on Saturdays.  No working is permitted on Sundays, Bank or Public Holidays.  The only current variations to these hours cover:  (i) the period until 22 November 2014 for works being undertaken in the rural section (Ch. 2000-5400) on Saturdays between the hours of 13.00 – 18.00; (ii) the period until 21 November 2014 for works being undertaken in the rural section (Ch. 2000-5400) on Mondays to Fridays between the hours of 19.00 – 20.00; and (iii) the period until 23 November 2014 for works being undertaken during approved railway possessions from Network Rail, between the hours of 00.00 – 07.00.  These additional hours were subject to separate approvals on 22 August 2014 and 19 September 2014.

You are now seeking approval to carry out:  (A) piling works at Ninfield Bridge between the hours of 13.00 and 18.00 on Saturdays from 1 November until 29 November 2014; and (B) sheet piling works in the Railway Cutting between the hours of 13.00 and 18.00 on Saturdays from 1 November until 20 December 2014.

/Continued

-2-	24 October 2014

You have indicated that the reason for the request to work outside the hours specified in Condition 11 of the planning permission is twofold.  Firstly, with regard to the Ninfield Bridge piling works, the process will take more than half a day to complete one pile and, therefore, the extended hours will enable a pile to be completed – thereby avoiding design and safety implications.  Secondly, with regard to the Railway Cutting sheet piling works, you have confirmed that recent bad weather has resulted in the cutting flooding, which has delayed the programme.  The additional hours in this area will mitigate the delays encountered from the bad weather.

You have confirmed that artificial lighting will be used for both activities, but that these will be positioned with the lights facing away from any residential properties.

The planned plant/equipment/resources involved in the Ninfield Bridge piling works will be as follows:

- 1no. Rotary bore piling rig;

- 1no. 70t crawler crane;

- 1no. 13t excavator and driver;

- 1no. 6t dumper and driver;

- Concrete delivery wagons;

- 4no.piling operatives

- Grab lorry

The planned plant/equipment/resources involved in the Railway Cutting sheet piling works will be as follows:

- 1no. 160t Crawler crane;

- 1no. Silent piler rig;

- 1no. 9t Dumper and driver;

- 1no. 13t excavator and driver;

- 1no. 3t excavator; and

- 4no. x piling operatives.

It has been confirmed that local residents in the vicinity of the works will be notified of the intended works in advance of them taking place.

I have given consideration to this request and taken into account the nature of the works proposed and the potential impact of the works on the amenity of local residents, as well as the original reason for this condition.  I have also considered the length of time you have requested and consider that there is scope for these works to be undertaken outside of the construction hours approved under Condition 11.  Consequently, in accordance with the powers delegated to me and pursuant to the provisions within Condition 11 of the above planning permission, I hereby APPROVE the works detailed in your letter and referred to above being carried out during the following hours:

- Ninfield Bridge – Piling Works: between the hours of 13.00 and 18.00 on Saturdays from 1 November until 29 November 2014; and

- Railway Cutting – Sheet Piling Works: between the hours of 13.00 and 18.00 on Saturdays from 1 November until 20 December 2014.

/Continued

-3-	24 October 2014

For the avoidance of doubt, this approval relates SOLELY to the piling works in the Railway Cutting and Ninfield Bridge.  Any additional working arrangements outside the approved hours detailed above, or for works not listed above, will be subject to further review and will require agreement in writing from the Head of Planning.

Please note that if at any time the activities being carried out in these extended hours give rise to justifiable complaint, or demonstrable harm to amenity, I reserve the right to withdraw this temporary amendment to the permitted working hours.  Please also note that should you received any complaints, you should notify Sarah Iles on Lewes (01273) 481631 within two working days of receiving the complaint.

Yours sincerely

Tony Cook

Tony Cook

Head of Planning

- Copy for Statutory Planning Register c/o Hastings Borough Council and Rother District Council, Your Ref RR/07/1488 - HS/07/444

- Amanda Parks Technical Assistant

- Bob Pape – East Sussex County Council (via email only)

- Chloe DeRenzy-Martin – East Sussex County Council (via email only)

condapprove.doc